## Asmita
Agile Task Board
Assigned To: | Asmita Chandrakar
Use Case: | Customer
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in the MVC project and Introducion to Azure and Creation of Virtual Machines | 3 | 4 | 2019-11-04 | 2019-11-04 | There were issues faced in creating virtual machines like unable to connect to the IP, and we were asked to delete the Virtual Machines by our mentor as we used Capgemini credentials for Azure portal without informing our mentor. Azure credentials would be given on the next day by our mentor.
Creation of SQL Database in Azure | 2 | 2 | 2019-11-05 | 2019-11-05 | We created a Sql Database in Azure and through IP we were able to use this Database in Sql Server Management Studio. There weren't too many issues as the proceedure is same as creating Virtual Machine. After creating database we accessed it and also deleted it as per the instructions of our mentor and we have screenshots of each step in the process.
Expecting Script for Table and Storedprocedure | 1 | 1 | 2019-11-06 | 2019-11-06 | As we can not access the Database on our computers due to some block so we have to use it on Trainers PC
Creation of APP Service | 1 | 1 | 2019-11-06 | 06-112019
Learning to create Active Diectory | 2 | 2 | 2019-11-07 | 2019-11-07
Learning to create Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07
Publishing MVC application on Azure App services | 2 | 2 | 2019-11-06 | 2019-11-06 | A few problem faced related to connection string in Entity framework and mode
Creating function through Azure function App | 1 | 1 | 2019-11-08 | 2019-11-08
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.5 | 2019-11-08 | 2019-11-08
Creating Azure web Cognitive services | 1 | 1 | 2019-11-09 | 2019-11-09
Creating HTML page to consume azure web Cognitive services | 0.5 | 0.5 | 2019-11-09 | 2019-11-09
Writing java Script code to save the key as cookie and ceating drop down as result | 2 | 4 | 2019-11-09 | 2019-11-09 | Problem with handling JSON and a few teachnical error related to CDN
Learning VSTS | 3 | 3 | 2019-11-11 | 2019-11-11
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-12 | 2019-11-12
developing web api and deploying it in azure | 3 | 4 | 2019-11-13 | 2019-11-13 | Deploying issues

## Tarunsree
Agile Task Board
Assigned To: | Tarunsree
Use Case: | Credit Card
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in the MVC project and Introducion to Azure and Creation of Virtual Machines | 3 | 4 | 2019-11-04 | 2019-11-04 | There were issues faced in creating virtual machines like unable to connect to the IP, and we were asked to delete the Virtual Machines by our mentor as we used Capgemini credentials for Azure portal without informing our mentor. Azure credentials would be given on the next day by our mentor.
Creation of SQL Database in Azure | 2 | 2 | 2019-11-05 | 2019-11-05 | We created a Sql Database in Azure and through IP we were able to use this Database in Sql Server Management Studio. There weren't too many issues as the proceedure is same as creating Virtual Machine. After creating database we accessed it and also deleted it as per the instructions of our mentor and we have screenshots of each step in the process.
Expecting Script for Table and Storedprocedure | 1 | 1 | 2019-11-06 | 2019-11-06 | As we can not access the Database on our computers due to some block so we have to use it on Trainers PC
Creation of APP Service | 1 | 1 | 2019-11-06 | 06-112019
Learning to create Active Diectory | 2 | 2 | 2019-11-07 | 2019-11-07
Learning to create Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07
Publishing MVC application on Azure App services | 2 | 2 | 2019-11-06 | 2019-11-06 | A few problem faced related to connection string in Entity framework and mode
Creating function through Azure function App | 1 | 1 | 2019-11-08 | 2019-11-08
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.5 | 2019-11-08 | 2019-11-08
Creating Azure web Cognitive services | 1 | 1 | 2019-11-09 | 2019-11-09
Creating HTML page to consume azure web Cognitive services | 0.5 | 0.5 | 2019-11-09 | 2019-11-09
Writing java Script code to save the key as cookie and ceating drop down as result | 2 | 4 | 2019-11-09 | 2019-11-09 | Problem with handling JSON and a few teachnical error related to CDN
Learning VSTS | 3 | 3 | 2019-11-11 | 2019-11-11
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-12 | 2019-11-12
developing web api and deploying it in azure | 3 | 4 | 2019-11-13 | 2019-11-13 | Deploying issues

## Akash
Agile Task Board
Assigned To: | Akash
Use Case: | Account
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in the MVC project and Introducion to Azure and Creation of Virtual Machines | 3 | 4 | 2019-11-04 | 2019-11-04 | There were issues faced in creating virtual machines like unable to connect to the IP, and we were asked to delete the Virtual Machines by our mentor as we used Capgemini credentials for Azure portal without informing our mentor. Azure credentials would be given on the next day by our mentor.
Creation of SQL Database in Azure | 2 | 2 | 2019-11-05 | 2019-11-05 | We created a Sql Database in Azure and through IP we were able to use this Database in Sql Server Management Studio. There weren't too many issues as the proceedure is same as creating Virtual Machine. After creating database we accessed it and also deleted it as per the instructions of our mentor and we have screenshots of each step in the process.
Expecting Script for Table and Storedprocedure | 1 | 1 | 2019-11-06 | 2019-11-06 | As we can not access the Database on our computers due to some block so we have to use it on Trainers PC
Creation of APP Service | 1 | 1 | 2019-11-06 | 06-112019
Learning to create Active Diectory | 2 | 2 | 2019-11-07 | 2019-11-07
Learning to create Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07
Publishing MVC application on Azure App services | 2 | 2 | 2019-11-06 | 2019-11-06 | A few problem faced related to connection string in Entity framework and mode
Creating function through Azure function App | 1 | 1 | 2019-11-08 | 2019-11-08
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.5 | 2019-11-08 | 2019-11-08
Creating Azure web Cognitive services | 1 | 1 | 2019-11-09 | 2019-11-09
Creating HTML page to consume azure web Cognitive services | 0.5 | 0.5 | 2019-11-09 | 2019-11-09
Writing java Script code to save the key as cookie and ceating drop down as result | 2 | 4 | 2019-11-09 | 2019-11-09 | Problem with handling JSON and a few teachnical error related to CDN
Learning VSTS | 3 | 3 | 2019-11-11 | 2019-11-11
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-12 | 2019-11-12
developing web api and deploying it in azure | 3 | 4 | 2019-11-13 | 2019-11-13 | Deploying issues

## Shobhit
Agile Task Board
Assigned To: | Shobhit
Use Case: | Employee
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in the MVC project and Introducion to Azure and Creation of Virtual Machines | 3 | 4 | 2019-11-04 | 2019-11-04 | There were issues faced in creating virtual machines like unable to connect to the IP, and we were asked to delete the Virtual Machines by our mentor as we used Capgemini credentials for Azure portal without informing our mentor. Azure credentials would be given on the next day by our mentor.
Creation of SQL Database in Azure | 2 | 2 | 2019-11-05 | 2019-11-05 | We created a Sql Database in Azure and through IP we were able to use this Database in Sql Server Management Studio. There weren't too many issues as the proceedure is same as creating Virtual Machine. After creating database we accessed it and also deleted it as per the instructions of our mentor and we have screenshots of each step in the process.
Expecting Script for Table and Storedprocedure | 1 | 1 | 2019-11-06 | 2019-11-06 | As we can not access the Database on our computers due to some block so we have to use it on Trainers PC
Creation of APP Service | 1 | 1 | 2019-11-06 | 06-112019
Learning to create Active Diectory | 2 | 2 | 2019-11-07 | 2019-11-07
Learning to create Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07
Publishing MVC application on Azure App services | 2 | 2 | 2019-11-06 | 2019-11-06 | A few problem faced related to connection string in Entity framework and mode
Creating function through Azure function App | 1 | 1 | 2019-11-08 | 2019-11-08
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.5 | 2019-11-08 | 2019-11-08
Creating Azure web Cognitive services | 1 | 1 | 2019-11-09 | 2019-11-09
Creating HTML page to consume azure web Cognitive services | 0.5 | 0.5 | 2019-11-09 | 2019-11-09
Writing java Script code to save the key as cookie and ceating drop down as result | 2 | 4 | 2019-11-09 | 2019-11-09 | Problem with handling JSON and a few teachnical error related to CDN
Learning VSTS | 3 | 3 | 2019-11-11 | 2019-11-11
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-12 | 2019-11-12
developing web api and deploying it in azure | 3 | 4 | 2019-11-13 | 2019-11-13 | Deploying issues

## Siddharth
Agile Task Board
Assigned To: | Siddharth
Use Case: | Loans
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in the MVC project and Introducion to Azure and Creation of Virtual Machines | 3 | 4 | 2019-11-04 | 2019-11-04 | There were issues faced in creating virtual machines like unable to connect to the IP, and we were asked to delete the Virtual Machines by our mentor as we used Capgemini credentials for Azure portal without informing our mentor. Azure credentials would be given on the next day by our mentor.
Creation of SQL Database in Azure | 2 | 2 | 2019-11-05 | 2019-11-05 | We created a Sql Database in Azure and through IP we were able to use this Database in Sql Server Management Studio. There weren't too many issues as the proceedure is same as creating Virtual Machine. After creating database we accessed it and also deleted it as per the instructions of our mentor and we have screenshots of each step in the process.
Expecting Script for Table and Storedprocedure | 1 | 1 | 2019-11-06 | 2019-11-06 | As we can not access the Database on our computers due to some block so we have to use it on Trainers PC
Creation of APP Service | 1 | 1 | 2019-11-06 | 06-112019
Learning to create Active Diectory | 2 | 2 | 2019-11-07 | 2019-11-07
Learning to create Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07
Publishing MVC application on Azure App services | 2 | 2 | 2019-11-06 | 2019-11-06 | A few problem faced related to connection string in Entity framework and mode
Creating function through Azure function App | 1 | 1 | 2019-11-08 | 2019-11-08
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.5 | 2019-11-08 | 2019-11-08
Creating Azure web Cognitive services | 1 | 1 | 2019-11-09 | 2019-11-09
Creating HTML page to consume azure web Cognitive services | 0.5 | 0.5 | 2019-11-09 | 2019-11-09
Writing java Script code to save the key as cookie and ceating drop down as result | 2 | 4 | 2019-11-09 | 2019-11-09 | Problem with handling JSON and a few teachnical error related to CDN
Learning VSTS | 3 | 3 | 2019-11-11 | 2019-11-11
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-12 | 2019-11-12
developing web api and deploying it in azure | 3 | 4 | 2019-11-13 | 2019-11-13 | Deploying issues